## Work Item Backlog
|  | date |  | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-04 | 2026-02-11 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-27 | 2026-06-03 | 2026-06-10
|  | done (cumulative) |  | 2026-01-07: 0; 2026-01-14: 3; 2026-01-21: 9; 2026-01-28: 9; 2026-02-04: 11; 2026-02-11: 14; 2026-02-18: 24; 2026-02-25: 35; 2026-03-04: 40; 2026-03-11: 49; 2026-03-18: 50; 2026-03-25: 52; 2026-04-01: 58
|  | items remaining |  | 2026-01-07: 51; 2026-01-14: 48; 2026-01-21: 42; 2026-01-28: 44; 2026-02-04: 42; 2026-02-11: 40; 2026-02-18: 33; 2026-02-25: 25; 2026-03-04: 20; 2026-03-11: 11; 2026-03-18: 10; 2026-03-25: 9; 2026-04-01: 3
|  | done this week |  | 2026-01-14: 3; 2026-01-21: 6; 2026-01-28: 0; 2026-02-04: 2; 2026-02-11: 3; 2026-02-18: 10; 2026-02-25: 11; 2026-03-04: 5; 2026-03-11: 9; 2026-03-18: 1; 2026-03-25: 2; 2026-04-01: 6
|  | new items |  | 2026-01-14: 0; 2026-01-21: 0; 2026-01-28: 2; 2026-02-04: 0; 2026-02-11: 1; 2026-02-18: 3; 2026-02-25: 3; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 1; 2026-04-01: 0
|  | Total items |  | 2026-01-07: 51; 2026-01-14: 51; 2026-01-21: 51; 2026-01-28: 53; 2026-02-04: 53; 2026-02-11: 54; 2026-02-18: 57; 2026-02-25: 60; 2026-03-04: 60; 2026-03-11: 60; 2026-03-18: 60; 2026-03-25: 61; 2026-04-01: 61
|  | extrapolated ship date |  | 2026-01-14: 2026-05-06; 2026-01-21: 2026-03-27 08:00; 2026-01-28: 2026-06-09; 2026-02-04: 2026-06-14 16:00; 2026-02-11: 2026-06-18 06:33; 2026-02-18: 2026-05-06; 2026-02-25: 2026-04-13 02:46; 2026-03-04: 2026-04-09 03:06; 2026-03-11: 2026-03-28 07:48; 2026-03-18: 2026-04-04 01:45; 2026-03-25: 2026-04-10 12:00; 2026-04-01: 2026-04-06 06:00
ID | Rank | Title | Est.
1211 | 33 | Audio In Level indicator (db sampled n times per second, where n = small, like 1) | 1 | 2026-02-11: 1; 2026-02-18: 0
1221 | 66 | Provide ability to export and import local contact metadata | 2 | 2026-01-28: 1; 2026-02-04: 0; 2026-02-11: 0
1090 | 100 | User must be able to add a channel | 3 | 2026-01-07: 1; 2026-01-14: 0; 2026-01-21: 0; 2026-01-28: 0; 2026-02-04: 0; 2026-02-11: 0; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1091 | 200 | Place a call by typing in a user name | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 0; 2026-01-28: 0; 2026-02-04: 0; 2026-02-11: 0; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1152 | 300 | Missing units should not block execution | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 0; 2026-01-28: 0; 2026-02-04: 0; 2026-02-11: 0; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1092 | 400 | Hang up the call | 3 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 0; 2026-01-28: 0; 2026-02-04: 0; 2026-02-11: 0; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1098 | 500 | Sign-in and -out with a name | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 0; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1202 | 575 | Persist Channels (Persist channel unit mappings to disk) | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 0; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1230 | 650 | Single Sign On: signing into Controller with Id signs in to each persisted channel | 3 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
674 | 700 | Display list of Contacts | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1153 | 800 | Reflect when call status flags change | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1208 | 900 | Add index number for each channel | 3 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1234 | 1000 | Live status of unit connections | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 0; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1240 | 1000 | Filter contacts - No Facebook contacts, blocked contacts or contacts with no Names in the retrieved Contacts list in Controller | 2 | 2026-02-18: 1; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1235 | 1100 | Add a combo box to call a Contact on any channel | 3 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1207 | 1200 | Technical Call Info (minimal info useful for operators to be assured that the STU is working properly: talk to Carl, Jamie, Chris and Marc to see what these are) | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1210 | 1300 | Search and add a new contact to contact list | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1209 | 1400 | Audio In and Out Level indicators | 3 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1255 | 1450 | Enumeration for operator display mode | 1 | 2026-02-18: 1; 2026-02-25: 0; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1205 | 1500 | Edit metadata (single free-form text element only) | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1241 | 1550 | Trace ability in Control | 3 | 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
478 | 1600 | Preview outgoing video on Control | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 1; 2026-03-18: 1; 2026-03-25: 1; 2026-04-01: 0
1204 | 1700 | Search local cached contacts, display Display Name and ID | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1212 | 1800 | Take snapshot and video fallback options | 3 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 0; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
480 | 1875 | Configure some Client settings from Controller | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 1; 2026-03-18: 1; 2026-03-25: 1; 2026-04-01: 0
613 | 1900 | Show status for contacts dynamically | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 0; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
606 | 1925 | Show hangup button on Contacts who are on a call | 3 | bar: 2026-01-07 to 2026-04-01
718 | 1950 | Set/unset contact as Favourite | 1 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 1; 2026-03-18: 0; 2026-03-25: 0; 2026-04-01: 0
1256 | 1975 | List favourite contacts at the top of the displayed contacts | 2 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 1; 2026-03-18: 1; 2026-03-25: 0; 2026-04-01: 0
1259 | 2050 | Controller : Redial last caller on each channel | 3 | 2026-01-07: 1; 2026-01-14: 1; 2026-01-21: 1; 2026-01-28: 1; 2026-02-04: 1; 2026-02-11: 1; 2026-02-18: 1; 2026-02-25: 1; 2026-03-04: 1; 2026-03-11: 1; 2026-03-18: 1; 2026-03-25: 1; 2026-04-01: 0
1347 | 2060 | Demo Essentials for NAB: Channel Refresh and Remove | 1 | 2026-03-25: 1; 2026-04-01: 0
CUT LINE (will not be done by show date: Apr 11)

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General